## Slide 1
Leadership Project Update
June 2026 · All entities · All sprints
Project Insights · Sequel Ortho

## Slide 2
Portfolio Summary
June 2026 — latest reported status per project
181
PROJECTS IN SCOPE
17
AT RISK (Y/R OR BLOCKED)
0
BLOCKED ON A DEPENDENCY
Sponsor | Scope G / Y / R | Schedule G / Y / R | Budget G / Y / R
Ann Wright | 3 / 0 / 0 | 1 / 1 / 1 | 1 / 2 / 0
Beth Gard | 4 / 0 / 0 | 2 / 2 / 0 | 4 / 0 / 0
Brandon Quindt | 1 / 0 / 0 | 0 / 0 / 1 | 0 / 0 / 1
Chris Denney | 1 / 0 / 0 | 1 / 0 / 0 | 1 / 0 / 0
Heather Clinton | 5 / 0 / 0 | 0 / 5 / 0 | 5 / 0 / 0
Jeremy Warren | 1 / 0 / 0 | 1 / 0 / 0 | 1 / 0 / 0
John Bring | 4 / 2 / 0 | 4 / 1 / 1 | 4 / 2 / 0
Katie Benak | 3 / 0 / 0 | 2 / 1 / 0 | 2 / 1 / 0
Kelly Feuker | 2 / 0 / 0 | 2 / 0 / 0 | 2 / 0 / 0
Tara Wisdom | 2 / 0 / 0 | 1 / 0 / 1 | 1 / 0 / 1

## Slide 3
Status — Sprint 0
S = scope · Sch = schedule · B = budget · latest monthly report
Project | PM | S | Sch | B | Prog. | Root cause | Notes
1. Qualtrics Implementation (1) - Up by April 1st (Angeliqu… | Heather Cramer | G | G | G | 99% | Time Estimate to Complete | • NOTES: Project has gone live. Surveys have transitioned. Final hang up on texting is sitting with legal ri…

## Slide 4
Status — Sprint 1 (Jan 12 - Feb 20)
S = scope · Sch = schedule · B = budget · latest monthly report
Project | PM | S | Sch | B | Prog. | Root cause | Notes
1 - Website Refresh* | Bill Citro | G | G | G | 80% | – | • NOTES: Tracking to May / June Launch. - Including FVO update on this platform. Launch in August with some …
1. Insurance Broker RFP* | Samantha Brezack | G | G | G | 50% | – | Part of 100 Day Plan - Draft RFP created, evaluation matrix completed, internal meetings start next week. 6 R…
1. Work Comp Portal Implementation* | Bill Citro | G | R | R | 5% | IT Resource Constraint | • NOTES: Capital approved, contract has not been signed - Internal IT has put a hold on the contract. 3rd p…
4. It's Your… (Neck/Hip/Spine)* | Miranda Harrahill | G | Y | G | 90% | – | •Successes –Changes have been pushed out. • Control plan has been defined and data will be reviewed in 30 d…

## Slide 5
Status — Sprint 2 (Mar 9 - Apr 10)
S = scope · Sch = schedule · B = budget · latest monthly report
Project | PM | S | Sch | B | Prog. | Root cause | Notes
1. Rev-Cycle automation | – | G | Y | G | 0% | – | • NOTES: ONI HOLD Meeting scheduled to meet with IT to detemine feasibility. • PROJECT RISKS & RECOMMENDATI…
2 - Ask A Hand Surgeon Hotline | Nichole Beran | G | G | Y | 45% | – | • NOTES: Met with Dr. Gaddie. Working on process and timeline as well as definifn KPIs. Katie B will reach…
5. Recipe Update Process (Adding pictures, etc.)/SPM Scan | McDonald, Shannon | G | Y | G | 50% | – | Meetings ongoing. Evaluating processes and potential solutions. - Feedback received at last OR performance m…

## Slide 6
Status — Sprint 3 (May 4 - Jun 12)
S = scope · Sch = schedule · B = budget · latest monthly report
Project | PM | S | Sch | B | Prog. | Root cause | Notes
1. Marking individual instruments (SPD) | McDonald, Shannon | G | G | G | 90% | – | • NOTES: Presented options to OR Performacne and will be trialing once samples come in from vendor. Vendor ha…
1.Extended Overflow Process/Protocols | Kristina Miller | G | G | G | 20% | – | • NOTES: Data collected focusing on 4th quarter as this project will mirror the levers pulled for busy season…
2. DocuStream | Katie Gardner | G | Y | G | 10% | – | • NOTES: Project charter created and PM identified. Meetings scheduled. • PROJECT RISKS & RECOMMENDATIONS: …
3 - Naming the Patient Pathway | Danielle Kleber | G | Y | G | 10% | – | • NOTES: Charter created, documentation collected by PM. Delay in start, no further delays expected. • PRO…
Wired Call Light System Upgrade (Capital Only) | Ann Wright | G | G | Y | 85% | – | • NOTES: Biomed is making great progress in identifying the issues and is hopeful that we will not have to re…

## Slide 7
Status — Unscheduled
S = scope · Sch = schedule · B = budget · latest monthly report
Project | PM | S | Sch | B | Prog. | Root cause | Notes
1. AIHealth Implementation | Tiffany Ketelsen | G | Y | G | 60% | – | • NOTES: • Successes – OrthoNebraska workflows being replicated in sandbox to test in new environment. Testi…
1. Expand Cyber Security Controls | Fortified | G | Y | G | 80% | IT Resource Constraint | • NOTES: Success: Completed VTM set up, Penetration Tests, and started roll out of MDR - Sentinel One. Challe…
1. Patient Access Intake | Bill Citro | G | Y | G | 85% | Time Estimate to Complete | • NOTES: Maple, Aksarben and 110 are complete. Access is saving roughly 6 mins per new patient. • PROJECT …
1. PMMC Contract Management - ACTIVE | Drew Feuerbach | G | Y | G | 88% | 3rd Party Vendor | Successes – Contracts are good to go, just pending data. Successes – Majority of data is completed Success -…
1. Sequel IQ - ACTIVE | Nate Heng | G | G | G | 50% | – | • NOTES: • Fox Valley Integration underway • Initial OrthoNebraska data integrated • PROJECT RISKS & RECOMME…
1. Workday Implementation | – | G | G | G | 75% | – | • NOTES: Progressing well and on budget. Current focus is on procurement and inventory work streams. Risks to…
1.DeliverHealth Interfaces | – | G | R | Y | 0% | Legal / Contract | DeliverHealth SIU Filter configured for interim solution to share clinic visits and surgery schedules with p…
2. Arthrex | Lindsay Murdock | G | G | G | 95% | – | Live and testing workflows with surgeons to get surgeon feedback. Some minor technical troubleshooting with p…

## Slide 8
Status — Unscheduled (cont.)
S = scope · Sch = schedule · B = budget · latest monthly report
Project | PM | S | Sch | B | Prog. | Root cause | Notes
2. Microsoft 365 Conversion Assessment (2) | Tom Simmons | G | G | Y | 80% | – | • NOTES: Reached major milestone with phase 1 migration. 20 users have been setup on Sequel Ortho tenant and…
2. Opmed.ai (Potential Leantaas replacement) (2) | Michelle Stinnette | Y | R | G | 15% | Analytics Resource Constraint | • NOTES: Met to determine scheduling and wait list workflow. Potential replacement for HIQ/Leantaas with enc…
2. SPD Expansion | Luke Norvell | G | R | R | 25% | Time Estimate to Complete | • NOTES: Presented a phased approach to cabinet on 5/27 to protect schedule and budget concerns. Proposal go…
3. IT Support Model Review & Needs Assessment (3) | Ann Wright | Y | Y | Y | 50% | Other Resources Constraint | • NOTES: PM joining first week in May to assist with Organizational change management at FV Continue to revie…
4. Call Center AI (4) | Miranda Harrahill | G | G | G | 60% | – | • NOTES: Board approval received. Legal signed off and contract fully executed. Implementation project kick …
Compensation Market Assessment & Structure Evaluation | Samantha Brezack | G | G | G | 90% | – | • NOTES: Part of 100 Day Plan - Compensation review in progress for both OrthoNebraska & FVO. Areas of oppor…
Dodge Business Office | Luke Norvell | G | G | G | 45% | – | • NOTES: Construction has started and is on schedule for an October delivery) • PROJECT RISKS & RECOMMENDATI…

## Slide 9
Resource Constraints
PM double-bookings and shared-team demand vs capacity (~3 hrs/wk per flagged project)
Project Manager | Sprint | #
McDonald, Shannon | Sprint 3 (May 4 - Jun 12) | 6
Kristina Miller | Sprint 4 (Jun 29 - Aug 7) | 4
Anna Becker | Sprint 2 (Mar 9 - Apr 10) | 2
Bill Citro | Sprint 1 (Jan 12 - Feb 20) | 2
Chrissy Cattau | Sprint 5 (Aug 24 - Oct 2) | 2
Kristina Miller | Sprint 3 (May 4 - Jun 12) | 2
McDonald, Shannon | Sprint 2 (Mar 9 - Apr 10) | 2
Michael Roberts | Sprint 1 (Jan 12 - Feb 20) | 2
Michael Roberts | Sprint 2 (Mar 9 - Apr 10) | 2
Sprint | IT req. | IT util. | An. req. | An. util.
Sprint 1 (Jan 12 - Feb 20) | 9 | 19% | 3 | 19%
Sprint 2 (Mar 9 - Apr 10) | 10 | 21% | 1 | 6%
Sprint 3 (May 4 - Jun 12) | 5 | 11% | 2 | 13%
Sprint 4 (Jun 29 - Aug 7) | 3 | 6% | 0 | 0%
Sprint 5 (Aug 24 - Oct 2) | 1 | 2% | 1 | 6%
Sprint 0 | 2 | 4% | 1 | 6%

## Slide 10
Budget Readout — 2026 Impact
Expected vs actual, by entity (operational + capital, $)
Entity | Op. expected | Op. actual | Cap. expected | Cap. actual
Fox Valley | — | — | — | —
OrthoNebraska | $51,500 | — | $1,591,925 | —
Sequel Ortho | $1,021,542 | $120,000 | $3,056,250 | —
Unassigned | — | — | — | —
Total | $1,073,042 | $120,000 | $4,648,175 | —

## Slide 11
Blocked on Dependencies
Projects waiting on an incomplete Finish→Start predecessor
No projects are currently blocked. ✔