Project Insights

User Guide

Enterprise project portfolio management for Sequel Ortho

Version 1.1 · June 2026 · https://sequelorthoprojects.com

Contents

# 1. Welcome to Project Insights

Project Insights is the single source of truth for Sequel Ortho's enterprise project portfolio — the 181 projects across Sequel Ortho, OrthoNebraska, Fox Valley, Kansas, and Colorado that used to live in the manually-maintained 2026 Leadership Project Priorities workbook. Instead of one person hand-editing a spreadsheet, project managers submit updates directly, dependencies and resource conflicts are tracked in one place, and leadership materials generate themselves from live data.

The application is available to everyone in the organization at https://sequelorthoprojects.com. It works in any modern browser — nothing to install.

- Project managers — submit monthly status updates (on the web or via Excel), keep project details current, and record dependencies.

- Sponsors and functional leaders — review status, watch the dashboard, and spot resource conflicts before they bite.

- Leadership — pull the branded PowerPoint deck for monthly reviews, filtered to exactly the cut you need.

Note — Sign-in is currently open while the platform rolls out. Microsoft sign-in (Entra) can be switched on later without any change to how the app works.

# 2. A Quick Tour

The home page links to every surface, and the navigation bar at the top of every page gets you anywhere in one click:

| Surface | What it's for |
| --- | --- |
| Dashboard | Portfolio health at a glance — status distribution, trends, financial impact, throughput, and who owes a monthly update. |
| Projects | The full inventory. Search, filter, sort; open any project to see or edit its details, submit updates, and manage dependencies. |
| Timeline | Every active project laid across its 2026 sprint window, colored by current status. |
| Resources | Where projects compete for the same people — PM double-bookings and IT/Analytics demand vs. capacity per sprint. |
| Reports | Download the branded leadership deck (.pptx), filtered by entity, sprint, or at-risk. |
| Bulk Update (Excel) | Download a pre-filled status template, fill it offline, upload it back with a preview before anything is saved. |

# 3. The Dashboard

The dashboard is computed live from the latest reported status of every project. Definitions used throughout:

| Term | Definition |
| --- | --- |
| Active | Progress below 100%. Completed projects drop out of active views automatically. |
| At risk | Latest report shows Yellow or Red on any of Scope / Schedule / Budget — or the project is blocked. |
| Blocked | A recorded Finish → Start predecessor is not yet complete (see Dependencies, section 8). |
| Overdue update | An active project with no status report submitted this calendar month (or never). |
| n/r | Not yet reported — the project has no monthly status submission yet. |

## Reading the cards

- Current status (RYG) — one stacked bar each for Scope, Schedule, and Budget across all active projects, with green / yellow / red / not-reported counts.

- Status trend by reporting period — the same three bars for every reporting month, oldest first, so you can see the portfolio improving or degrading over time.

- 2026 operational impact by entity — expected vs. actual operational dollars. The header also shows the confidence-weighted total: each project's expected dollars multiplied by its probability of hitting them (a $100,000 project at 50% confidence contributes $50,000). Projects without a stated confidence count at face value.

- Throughput by sprint — completed vs. total projects per sprint; the bar fills as a sprint's projects finish.

- Overdue monthly updates — the chase list. Grouped by project manager, with each project's last-reported period. If you manage projects, keeping your name off this board is the goal; one quick update per project per month does it.

# 4. The Project Inventory

Open Projects to see the whole portfolio in one table.

- Search matches project name, sponsor, project manager, and strategic imperative as you type.

- Entity and Type filters narrow to one organization (e.g. OrthoNebraska) or one delivery type (Sprint, JDI, MGP, Capital Only).

- Sortable columns — click Project, Entity, PM, or % Complete headers to sort; click again to reverse.

- Status dots — the three dots in each row are the latest Scope / Schedule / Budget readings (grey = not yet reported). Hover for the label.

- Show archived — archived projects are hidden by default; tick the checkbox (it appears once anything is archived) to include them, marked with an amber Archived badge.

## Saved filters

Set up a view you use often (say, your own entity + Sprint type), type a name into “Save filter as…”, and click Save. The view re-applies any time from the “Saved filters…” dropdown; Delete removes the selected one.

Note — Saved filters are stored in your browser, so they're personal to you and to the computer you saved them on.

## The project page

Click any project name to open its detail page:

- Overview — sponsor, PM, team, sprint, priority, payoff quadrant, core process, resource flags, % complete.

- Objective & KPI and Financial Impact — the why and the dollars (expected/actual, 2026 and 2027, operational and capital, capital priority, confidence).

- Dependencies — what this project waits on and what waits on it (section 8).

- Status History — every monthly report ever submitted, newest first.

# 5. Submitting Your Monthly Update

This is the core PM workflow — it replaces emailing edits to the workbook owner. From a project page, click Submit monthly update.

1.  Confirm the reporting period (it defaults to the current month, e.g. “June 2026”).

2.  Set Scope, Schedule, and Budget to Green, Yellow, or Red (see the meanings below).

3.  If anything is Yellow or Red, pick the Root Cause and describe the Mitigation Plan.

4.  Update Progress (0–100%), the value statements, KPIs, and your notes for the month.

5.  Click Submit update. The report lands in the project's Status History immediately and flows to the dashboard, timeline, and leadership deck.

## What the colors mean

| Status | Meaning |
| --- | --- |
| Green | On track — proceeding as planned. |
| Yellow | Risks or minor issues need attention; mitigation is in motion. |
| Red | Serious problems threaten scope, schedule, or budget — leadership attention needed. |

## Root causes

When a status is Yellow or Red, pick the dominant driver: IT Resource Constraint · Analytics Resource Constraint · Other Resources Constraint · Time Estimate to Complete · Funding · 3rd Party Vendor · Legal / Contract · Scope Creek. These feed the resource-contention views, so an accurate pick matters.

Note — Each submission is a new record, so the trend view stays honest. Made a mistake? Any report can be edited or deleted afterwards — see section 8, Correcting & Removing Data.

# 6. Editing Project Details

From a project page, click Edit to change the structured fields: name, department, entity, strategic imperative, sponsor, PM, team, sprint, type, priorities, core process, % complete, confidence, objective, goal, KPI, and notes. Picking a person or category not yet in the lists simply adds it.

The Financials & Scheduling section covers everything that used to live only in the workbook's money columns: capital-project flag and spend quarter, capital priority, JDI / MGP quarters and duration, and the eight expected/actual operational and capital dollar fields for 2026 and 2027 — so every imported value can be corrected in place.

Note — Percent complete on the project is the baseline figure; the progress you report in a monthly update supersedes it in dashboards once submitted.

# 7. Bulk Updates with Excel

If you prefer working offline — or you're updating many projects at once — use Bulk Update (Excel) from the Projects page or home page.

1.  Optionally choose a Project Manager so the template contains only their projects, then click Download template.

2.  Fill in the status columns in Excel. Every row is pre-filled with the Project ID, name, and current period; the RYG and Root Cause columns have dropdowns so values stay valid. Progress is entered 0–100.

3.  Back in the app, choose the file and click Preview. Every row is checked and shown as ready or error with the specific problem — nothing is saved yet.

4.  Fix any errors in Excel and re-upload, then click Commit to save all ready rows as monthly updates.

Note — Don't edit the Project ID or Project Name columns — they're how rows match back to projects. Rows you leave blank are simply skipped.

# 8. Correcting & Removing Data

Everything captured in Project Insights — imported from the workbook or entered since — can be corrected in place. No re-import needed.

## Fixing or removing a status report

In a project's Status History, every row has Edit and Delete actions. Edit opens the same form used to submit, pre-filled — change anything (including the period) and save; the row shows an (edited) marker afterwards. Delete asks for confirmation and permanently removes that one report; dashboards and decks immediately reflect the previous one.

## Archiving a project (the usual way to remove one)

At the bottom of each project page, Archive project hides the project from the inventory, dashboard, timeline, resources, decks, and Excel templates — without deleting anything. It stays reachable via the inventory's Show archived toggle, displays an amber banner, and can be Restored with one click. Use archive for canceled, on-hold, or deduplicated work — it preserves the record (this replaces the old habit of typing “CANCELED” into the project name).

## Deleting a project permanently

Permanent deletion is reserved for true mistakes — duplicates or test entries. It is intentionally two steps: archive the project first, then choose Delete permanently… and type the project's exact name to confirm. This removes the project together with its entire status history and dependency links, and it cannot be undone.

Note — Rule of thumb (standard practice in portfolio tools): archive when the work mattered, delete only when the record never should have existed.

# 9. Dependencies

Dependencies capture what the workbook never could: which projects wait on which. Each project page has a Dependencies panel with two lists — what it depends on (upstream) and what it blocks or feeds (downstream).

## Adding one

1.  Choose the direction: “This project depends on…” or “This project blocks/feeds…”.

2.  Pick the other project and the dependency type (below); optionally add lag days and a note.

3.  Click Add dependency.

| Type | Use it when… |
| --- | --- |
| Finish → Start | The other project must finish before this one can start (capability sequencing). This is the type that drives “Blocked” flags. |
| Start → Start | Both must kick off together (shared mobilization). |
| Resource contention | The projects compete for the same people — record it when you've agreed who yields. |
| Vendor | A shared third-party vendor gates progress. |
| Funding | Capital or budget approval upstream. |
| Legal / Contract | Contract execution or legal review gates the work. |
| Decision / Approval | Awaiting a governance or leadership decision. |
| Data | Needs data, an interface, or a report another project delivers. |

- Blocked badge — when a Finish → Start predecessor is incomplete, the dependent project shows a red “Blocked” badge on its page, the timeline (⛔), the dashboard counts, and the leadership deck.

- Cycle protection — the app refuses sequencing loops (A waits on B while B waits on A, even through intermediaries), so the schedule always has a workable order.

Note — Best practice: record dependencies at project kickoff, when they're known and cheap to write down — not when they've already bitten.

# 10. Resource Contention

The Resources page surfaces, before a sprint starts, what used to appear only afterwards as “IT Resource Constraint” root causes:

- PM double-bookings — any project manager with more than one active project in the same sprint, with the conflicting projects listed.

- Team capacity — the IT and Analytics teams' weekly project-work hours, from the workbook's staffing model (headcount × the share of each week available for project work).

- Sprint demand vs. capacity — how many active projects per sprint are flagged as needing IT or Analytics, and the implied utilization assuming roughly 3 hours/week per flagged project (the workbook's “medium” sizing). Amber means above 85%; red means demand exceeds capacity.

Use it during sprint planning: if Sprint 2 shows IT at 110%, something moves before the sprint starts — not after it fails.

# 11. The Timeline

The Timeline page draws every active project as a bar across its sprint window in 2026. Bar color is the worst of the project's latest Scope/Schedule/Budget (grey = not yet reported); ⛔ marks projects blocked on a dependency. Projects in sprints without dates (Sprint 0, Sprint 7) are listed below the chart. Click any name to open the project.

# 12. Reports — the Leadership Deck

The Reports page generates a presentation-ready PowerPoint from live data — no more hand-assembled monthly decks. Choose an entity, a sprint, and/or “at-risk only”, then click Download deck.

The deck follows the SequelOrtho PowerPoint template (16:9, Montserrat, brand colors) and contains:

- Cover — period and the filters used.

- Portfolio Summary — projects in scope, at-risk and blocked counts, and the Green/Yellow/Red rollup by sponsor.

- Status by sprint — every reporting project with colored Scope/Schedule/Budget cells, progress, root cause, and notes.

- Resource Constraints — PM double-bookings and team demand vs. capacity.

- Budget Readout — expected vs. actual 2026 operational and capital dollars by entity, with totals.

- Blocked on Dependencies — what's waiting and on what.

Note — The “at-risk only” cut is ideal for exception-based reviews: a deck containing nothing but the projects that need the room's attention.

# 13. Tips & Troubleshooting

- Everything is live. Pages and decks read the database at the moment you open them — submit an update and it's in the next deck.

- Downloads open in Word/Excel/PowerPoint. If your browser has an “Office editing” extension that tries to open files in Google Docs, this guide's download already routes around it; exported templates and decks download as normal files.

- Who can edit? While sign-in is off, anyone with the link can edit — appropriate for the rollout phase. Once Microsoft sign-in is enabled, edits require an organizational account and updates are attributed to the submitter.

- Saved filters are per-browser. They're not shared with colleagues; everyone curates their own.

- A project is missing? Check the search box and filters first — and tick Show archived, in case it was archived. If it's genuinely absent, ask the portfolio administrator.

# Appendix — For Administrators

The platform is operated from the project repository (buckygrad/project-insights). Day-to-day administration:

- Workbook import — npm run import:workbook -- "<path>.xlsx" loads projects and LP status sheets. Add --dry for a parse report with no writes. A full re-import refuses to wipe user-entered dependencies unless --force is given.

- Capacity refresh — npm run import:workbook -- "<path>.xlsx" --capacity-only reloads the IT/Analytics staffing model without touching projects, status, or dependencies.

- Vocabularies — entities, strategic imperatives, categories, sprints, and root causes are seeded by npm run db:seed and grow automatically when editors introduce new values.

- Deployment — merging to main runs the test gate and auto-deploys to Netlify. Configuration (database URL, auth mode) lives in site environment variables; see docs/go-live.md in the repository.

- Turning on Microsoft sign-in — register an Entra application, set the AUTH_* variables, and switch AUTH_MODE to “entra” (runbook step 4 in docs/go-live.md).

Questions or ideas? The portfolio team owns this guide — regenerate it with npm run build:user-guide after editing scripts/build-user-guide.mjs.